## Launch Checklist
VH Solar Scheduler — Launch Checklist
Everything needed to go from prototype to production
1. DATA EXPORTS FROM SALESFORCE
| Task | Status | Owner | Details | ETA
✓ | Trailing Appt by Sales Rep (96K records) | DONE | Adam | Uploaded. Appointment history by rep and status. | Done
✓ | IS Completed by State & Date (34K records) | DONE | Adam | Uploaded. Daily completed sits by state, 3 years. | Done
✓ | Rep Roster / Depth Map (51 reps) | DONE | Adam | Uploaded. Live roster with constraints + home zips. | Done
✓ | Opportunity Report (17.5K deals, $612M) | DONE | Adam | Uploaded. Full deal history with amounts + system sizes. | Done
✓ | Sit Rate by Lead Source (112K appts) | DONE | Adam | Uploaded. Sit/no-sit/DQ by source, monthly. | Done
✓ | Trailing Completed Appointments (13K) | DONE | Adam | Uploaded. Completed appts Jan 2025+ with rep + lead source. | Done
☐ | Individual Appointment Rows (SOQL Query 1) | CRITICAL | Adam | Need individual rows with: date, time slot, rep, lead source, address, outcome. Summary reports are great but individual rows power the ML model. See SOQL tab for the exact query. | This week
☐ | Lost Opportunity Reasons (SOQL Query 2) | NEEDED | Adam | Closed_Lost_Reason__c on Opportunity. Helps predict which leads to prioritize and which to filter. | This week
☐ | Cancel / Reschedule Detail (SOQL Query 6) | TODO | Adam | Individual cancel/reschedule events with reason codes. Powers no-show prediction. | Week 2
2. GOOGLE WORKSPACE SETUP
| Task | Status | Owner | Details | ETA
☐ | Create Google Cloud project (vh-scheduler) | CRITICAL | Adam | console.cloud.google.com > New Project. Takes 2 min. | This week
☐ | Enable Google Calendar API | CRITICAL | Adam | In project: APIs & Services > Enable > 'Google Calendar API' | This week
☐ | Create OAuth 2.0 credentials | CRITICAL | Adam | APIs & Services > Credentials > OAuth client ID > Web app. Set redirect URI. | This week
☐ | Rep Google Calendar IDs (email list) | NEEDED | Adam | Each rep's calendar email (@venturehome.com). CSV or spreadsheet. | Week 2
☐ | Domain-wide delegation (Workspace admin) | NEEDED | Adam/IT | Lets scheduler read all rep calendars without individual auth. | Week 2
3. SALESFORCE CONNECTED APP
| Task | Status | Owner | Details | ETA
☐ | Create SF Connected App | NEEDED | Adam/SF Admin | Setup > App Manager > New Connected App. Note Consumer Key + Secret. | Week 2
☐ | Confirm custom field API names | NEEDED | Adam | Verify: Appointment_Status__c, Sales_Team__c, Lead_Source__c, Is_Reschedule__c. Screenshot of Object Manager > Event > Fields. | This week
☐ | Salesforce sandbox for testing | TODO | Adam/SF Admin | A sandbox org to test sync without touching production. | Week 2
4. INFRASTRUCTURE & DEPLOYMENT
| Task | Status | Owner | Details | ETA
✓ | Frontend app (React + Vite) | DONE | Claude | Calendar views, booking pages, territory filter, availability engine. | Done
✓ | Express backend skeleton | DONE | Claude | OAuth routes, calendar API proxy, mock/live toggle. | Done
✓ | Google Calendar mock layer | DONE | Claude | Mock free/busy + events matching GCal API v3 shapes. | Done
✓ | Partner booking pages (5 partners) | DONE | Claude | Greenwatt, Verse, SunLink, Lo Mano, Remix Dynamics. | Done
✓ | Real rep roster loaded (51 reps) | DONE | Claude | All reps with home zips, constraints, languages, hybrid flags. | Done
☐ | Cloud Run project + billing | TODO | Adam | gcloud projects create vh-scheduler + enable billing. | Week 2
☐ | Custom domain for booking links | TODO | Adam | e.g. book.venturehome.com. DNS + SSL. | Week 3
☐ | SMS / email service (Twilio + SendGrid) | TODO | Adam | For appointment confirmations and reminders. | Week 3
5. SCHEDULER FEATURES (Claude builds)
| Task | Status | Owner | Details | ETA
✓ | Territory zip-code auto-detection | DONE | Claude | Corrected for NYE/NYW split. All 7 territories mapped. | Done
✓ | Free/busy availability engine | DONE | Claude | Slot availability with consultant-level conflict detection. | Done
☐ | Predictive rep assignment model | CRITICAL | Claude | BLOCKED: needs individual appointment rows (SOQL Query 1). | After data
☐ | Demand forecasting (daily by territory) | TODO | Claude | Uses IS completed data. Can start NOW. | This week
☐ | No-show / cancellation prediction | TODO | Claude | Uses sit rate data. Can start NOW. | This week
☐ | Partner performance dashboard | TODO | Claude | Uses opportunity data. Can start NOW. | This week
☐ | Drive time optimization | TODO | Claude | BLOCKED: needs Google Maps API key. | Week 2
☐ | Live Google Calendar sync | TODO | Claude | BLOCKED: needs OAuth credentials. | Week 2
☐ | Live Salesforce sync | TODO | Claude | BLOCKED: needs Connected App. | Week 3
CRITICAL PATH: Appointment detail export > Predictive model > Google OAuth > Live sync > Deploy

## SOQL Queries
Copy & Paste These Into Salesforce Developer Console
CRITICAL — Appointment Detail (Query 1)
SELECT Id, Subject, OwnerId, Owner.Name, ActivityDate, StartDateTime, EndDateTime, DurationInMinutes, Location, Appointment_Status__c, Appointment_Status_Result__c, RecordType.Name, Sales_Team__c, Lead_Source__c, IsVirtual__c, Is_Reschedule__c, Appointment_Type__c, CreatedDate FROM Event WHERE RecordType.Name IN ('Appointments', 'SR Appointment') AND Don_t_count_for_reporting__c = false AND (NOT Account.Name LIKE '%test%') ORDER BY StartDateTime DESC
HIGH — Lost Opportunities (Query 2)
SELECT Id, Name, Owner.Name, StageName, Amount, CloseDate, IsWon, LeadSource, Account.BillingPostalCode, Sales_Team__c, Closed_Lost_Reason__c, Number_of_Appointments__c FROM Opportunity WHERE RecordType.Name = 'Venture' AND IsClosed = true AND (NOT Name LIKE '%test%') ORDER BY CloseDate DESC
MEDIUM — Cancel/Reschedule Log (Query 6)
SELECT Id, Owner.Name, Sales_Team__c, ActivityDate, StartDateTime, Appointment_Status_Result__c, Is_Reschedule__c, Reschedule_Reason__c, Cancel_Reason__c, Lead_Source__c FROM Event WHERE RecordType.Name IN ('Appointments', 'SR Appointment') AND Appointment_Status_Result__c IN ('Rescheduled', 'Not Completed') AND CreatedDate >= 2020-01-01T00:00:00Z ORDER BY StartDateTime DESC